{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["已开通航站","计划开通航站"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"已开通航站","index":0,"n_rows":31,"n_cols":4,"rows_kept":31,"cut":false,"hidden":false,"merged":[[8,3,21,3],[22,3,27,3],[28,3,30,3]]}
["序号","已开通航站","采集技术","开通时间"]
[1,"北京首都","RFID、BRS","2020-05-01"]
[2,"重庆","RFID","2020-05-01"]
[3,"成都双流","RFID、BRS","2020-11-01"]
[4,"武汉","RFID","2020-11-01"]
[5,"丽江","Manual Load","2020-11-01"]
[6,"昆明","RFID","2021-07-01"]
[7,"深圳","RFID","2021-09-01"]
[8,"郑州","RFID","2022-07-01"]
[9,"运城","Manual Load"]
[10,"达州","Manual Load"]
[11,"西昌","Manual Load"]
[12,"绵阳","Manual Load"]
[13,"张家界","Manual Load"]
[14,"九寨沟","Manual Load"]
[15,"大理","Manual Load"]
[16,"威海","Manual Load"]
[17,"湛江","Manual Load、RFID"]
[18,"银川","Manual Load"]
[19,"烟台","Manual Load"]
[20,"桂林","Manual Load"]
[21,"延吉","Manual Load"]
[22,"杭州","BRS","2022-10-01"]
[23,"天津","BRS"]
[24,"上海虹桥","BRS"]
[25,"上海浦东","BRS"]
[26,"温州","BRS"]
[27,"成都天府","BRS"]
[28,"青岛","RFID","2022-11-01"]
[29,"广州","RFID"]
[30,"贵阳","RFID"]

{"sheet":"计划开通航站","index":1,"n_rows":18,"n_cols":4,"rows_kept":18,"cut":false,"hidden":true,"merged":[[17,0,17,3]]}
["序号","计划开通航站","采集技术","计划开通时间"]
[1,"长沙","RFID","2023-06-01"]
[2,"乌鲁木齐","RFID","2023-06-02"]
[3,"西安","RFID","2023-06-03"]
[4,"海口","RFID","2023-06-04"]
[5,"济南","RFID","2023-06-05"]
[6,"南宁","RFID","2023-06-06"]
[7,"南昌","RFID","2023-06-07"]
[8,"石家庄","RFID","2023-06-08"]
[9,"北京大兴","RFID","2023-09-01"]
[10,"南京","RFID","2023-09-01"]
[11,"三亚","RFID","2023-09-01"]
[12,"厦门","RFID","2023-09-01"]
[13,"哈尔滨","RFID","2023-09-01"]
[14,"宁波","RFID","2023-09-01"]
[15,"呼和浩特","RFID","2023-09-01"]
[16,"太原","RFID","2023-09-01"]
["备注：计划开通航站不限于以上所列范围，产品服务部将根据各属地机场行李全流程跟踪系统建设进度、行李跟踪数据质量、各站点保障能力等情况进行动态调整。"]